## Sheet1
	Operational Requirement	Status	Working On
1	Must have off grid capability	Not Available	An, Melvin
2	Must have pre-installed software for quick installation	Incomplete	An, Melvin
3	Must be able to upload the data to S3 bucket	Satified	An
4	Must be able to control the sensors over the Home Assistant app	Not Available	An
5	Weather Station and Sensors have to be able to operate in outdoor environment	Not Available	An, Melvin
6	Must be display soil data on a station	Not Available	An
7	Must be able to 24/7 data update	Not Available

	Tasks Needed to deliver the kit	Status	Working On
5.1	Unmount the old Davis Weather Station	Incomplete
5.2	Mounting Wind Sensors on the Pole	Incomplete
5.3	Testing the 8 set of sensors	Incomplete
4.1	Spinning up EC2 for home assitant App.	Incomplete
4.2	Config MQTT for on-site Raspberry Pi 4 to connect EC2.	Incomplete
4.3	Write a Python script to produce JSON temperature of Raspberry Pi.	Incomplete
4.4	Test if the solar water is water resistant.	Incomplete

	Issues
	Public Policy	Status	Solution
1	Public Access on AWS S3	Solved	Turn off Public Access
2	Raspberry Pi 4 failure due to unknown reason	Unsolved	There is a possibility that the box doesn’t have water resistent capability