## Sheet1
| Operational Requirement | Status | Working On
1 | Must have off grid capability | Not Available | An, Melvin
2 | Must have pre-installed software for quick installation | Incomplete | An, Melvin
3 | Must be able to upload the data to S3 bucket | Satified | An
4 | Must be able to control the sensors over the Home Assistant app | Not Available | An
5 | Weather Station and Sensors have to be able to operate in outdoor environment | Not Available | An, Melvin
6 | Must be display soil data on a station | Not Available | An
7 | Must be able to 24/7 data update | Not Available
| Tasks Needed to deliver the kit | Status | Working On
5.1 | Unmount the old Davis Weather Station | Incomplete
5.2 | Mounting Wind Sensors on the Pole | Incomplete
5.3 | Testing the 8 set of sensors | Incomplete
4.1 | Spinning up EC2 for home assitant App. | Incomplete
4.2 | Config MQTT for on-site Raspberry Pi 4 to connect EC2. | Incomplete
4.3 | Write a Python script to produce JSON temperature of Raspberry Pi. | Incomplete
4.4 | Test if the solar water is water resistant. | Incomplete
Issues
| Public Policy | Status | Solution
1 | Public Access on AWS S3 | Solved | Turn off Public Access
2 | Raspberry Pi 4 failure due to unknown reason | Unsolved | There is a possibility that the box doesn’t have water resistent capability